Mixed Reality systems for real-time construction project monitoring to improve schedule performance

Abstract

Construction projects continue to face coordination inefficiencies, schedule pressure, and limited visibility of actual site conditions despite increasing investment in digital tools. This scoping review examines the use of mixed reality systems for inspection, real-time monitoring, coordination and schedule-oriented control of construction projects. A PRISMA-ScR-guided process and a PCC-framed review question were used to identify studies published between 2015 and 2025 through the ASCE Library, Scopus, IEEE Xplore, and Web of Science. These studies were then screened and charted in duplicate using a standardised template. Eighteen empirical studies were included, covering buildings, tunnelling, modular construction, bridges, mechanical, interior works, electrical, and plumbing and (MEP) installation. These studies found that XR workflows linked with BIM, SLAM/VSLAM, computer vision, mobile platforms, 4D scheduling, laser scanning, and robotic capture improved the resolution of issues, communication of designs, collaborative planning, visibility of progress, the efficiency of inspections, remote inspections, constructability reviews and the shared understanding of site conditions. Quantitatively, inspection efficiency improved by 78.63% in one study, coordination overhead fell by up to 75% in another, and one MR progress-monitoring system reported 97.3% recall, 96.5% precision, and 95.2% accuracy. However, deployment remains constrained by interoperability issues, user adoption, safety concerns, hardware limitations, and weak integration with formal project control systems. This review consolidates dispersed evidence and identifies priorities for workflow integration, field validation, and governance.

Keywords: Augmented reality (AR); Building information modelling (BIM), Mixed reality (MR); Virtual reality (VR).

  - Background

The problems of chronic cost escalation, schedule pressure, and inefficiency of coordination remain the real issues of construction projects, and thus, timely progress reporting is the only tool to have efficient project management. Studies on delays indicate that they are hardly ever caused by a single factor but rather as a result of failures in such areas as communication, resource availability, coordination, planning, financing, site management, and the quality of the execution (Durdyev & Hosseini, 2020). Similarly, quantitative data show that a significant percentage of delays in different projects relate to administrative failures, implementation challenges, labour disputes, mismanagement, construction flaws, financial problems, and relationship breakdowns (Viles et al., 2020). These circumstances render construction monitoring strategically significant, since low visibility of the real site situation restricts the capacities of the project teams to identify deviations in time, keep schedule commitments, and organise corrective actions.

This issue belongs to a broader trend of Construction 4.0, where digital technologies should significantly improve decision-making, productivity, and coordination at all stages of the project (Klinc & Turk, 2019; Forcael et al., 2020). Nevertheless, there is imbalanced digital maturity. There are indications that the design and planning have evolved at a much faster rate, but the execution is relatively less digitalised and partially automated. This is regardless of the fact that the stage where delays, rework, disruptions, and control failures are the most evident and expensive is the implementation phase (Begić et al., 2022). This is important because effective project control involves the production of digital information in the office as well as connecting this information to the changing site conditions in a manner that facilitates prompt managerial action.

Consequently, building research has increasingly investigated data-driven observation technologies that are able to document actual conditions and transform them into information on the state of a project. Computer vision has become a significant part of this development, and its uses are in defect inspection, progress monitoring, productivity tracking, safety monitoring, and performance analysis (Zhong et al., 2019; Paneru & Jeelani, 2021). But this literature shows incomplete fragmentation as well. The complexity of interior environments is further aggravated by the fact that incomplete visibility, clutter, dynamic task sequencing, and occlusion complicate the determination of reliable progress capture, particularly when dealing with fit-out and finishing operations, which tend to be time sensitive (Ekanayake et al., 2021). In a broader sense, vision-based, automated progress monitoring remains likely to use disconnected subprocesses to obtain data, estimate progress, retrieve information, and visualise it, and has a low level of interoperability and poor connectivity to real-world construction management processes (Sami Ur Rehman et al., 2022).

Recent research, hence, proposes a more integrated approach to the understanding of project progress, in which BIM is viewed as a managerial tool other than a distinct modelling programme. Integrating BIM with various monitoring technologies produces more comprehensive and precise status data as compared to separate sensing systems (Hasan & Sacks, 2023). In the meantime, the life-cycle study suggests that the management value of BIM is determined by the integration with the planning process, monitoring, and control (Wang & Chen, 2023). At the same time, the study of digital twins has increased the expectations of real-time, two-way, data-driven construction control, as well as emphasised the unsolved issues in terms of privacy and governance, scalability, interoperability, and data quality (Omrany et al., 2023). It is in this light that mixed reality is a central point of concern as it occupies an overlap between site-state capture, digital models, and operational decision support in schedule-based construction monitoring.

  - Scope of Review

The scoping review is devoted to the application of mixed reality and other related extended reality (XR) systems to real-time monitoring of construction, inspection, augmented reality (AR), and virtual reality (VR) applications, coordination, and schedule-based control in an active project setting. It includes construction, underground excavation, infrastructure, digital replicas, modular, 4D scheduling, MEP, and interior construction contexts where XR is combined with BIM, and site-capture technologies such as laser scanning, SLAM/VSLAM, drones, and computer vision. The review maps the characteristics of empirical studies published between 2015 and 2025, synthesising evidence on schedule-relevant performance gains, workflow architectures, and implementation constraints. Training-only, stand-alone visualisation and non-construction applications are beyond the scope of this review.

  - Aim and Specific Objectives

Aim: The aim is to map and synthesise the empirical evidence on the use of mixed reality systems for real-time construction monitoring and schedule-oriented control. Particular attention will be paid to workflow architecture, performance outcomes, and implementation conditions in active construction settings.

Objectives:

- Identify and describe the types of AR, MR, VR, and related XR workflows used for construction monitoring, inspection, coordination, and schedule control, and their integration with BIM, 4D scheduling, digital twins, and site-capture technologies.

- Synthesise the reported operational and schedule-relevant outcomes of these systems, particularly with regard to progress visibility, inspection efficiency, issue resolution, coordination, and project control decision-making.

- Examine the main implementation barriers, enabling conditions, and practical implications associated with deploying mixed reality systems in routine construction monitoring and control.

2. Methodology

2.1 Design and Reporting Standards

This scoping review employed the Population–Concept–Context (PCC) framework to map the characteristics, breadth, and implementation patterns of mixed reality systems used for real-time construction monitoring and schedule-oriented control. The review was reported in accordance with the PRISMA extension for scoping reviews (PRISMA-ScR), with transparent reporting of the screening, identification, inclusion, and eligibility decisions. No protocol registration was undertaken. In line with the scoping objective of mapping and classifying evidence rather than estimating pooled effects, no formal risk-of-bias or critical appraisal tool was applied. Methodological safeguards included a multi-database search strategy, explicit eligibility criteria, independent screening at the title/abstract and full-text stages, and standardised data charting.

2.2 Eligibility Criteria

Eligibility was defined using the PCC framework to ensure that the evidence included remained closely aligned with the aim of the review and the research questions. The review incorporated peer-reviewed empirical studies examining mixed reality or related immersive systems in construction settings, in which the technology was applied to tasks such as monitoring, coordination, inspection, schedule control, or progress tracking. Studies were included where XR workflows were linked with 4D scheduling, digital twins, BIM, or site-capture technologies such as SLAM/VSLAM, image-based capture, laser scanning, computer vision, or drones. Papers were included if they reported either direct schedule-related outcomes or operational performance indicators relevant to project control. Studies addressing generic visualisation only, training only, or non-construction settings without construction-ready validation were excluded. Table 1 presents the eligibility criteria applied in this review.

Table 1: Eligibility Criteria according to the PCC Framework

| Item | Inclusion Criteria | Exclusion Criteria |
| --- | --- | --- |
| Population | Construction projects, site operations, project teams, trades, and monitored building or infrastructure elements in active project environments | Non-construction populations; manufacturing, medical, military, education, or other non-construction settings without construction-ready validation |
| Concept | AR, MR, VR, or XR systems applied to construction monitoring, inspection, coordination, progress tracking, issue resolution, or schedule control; integration with BIM, 4D scheduling, digital twins, or capture technologies | XR used only for training, marketing, stakeholder presentation, or stand-alone visualization without monitoring/control relevance |
| Context | Building, infrastructure, tunnelling, industrial, modular, or interior construction settings; on-site or remote project monitoring during design-for-construction, execution, inspection, or coordination | Purely laboratory, classroom, or non-operational contexts with no construction task linkage |
| Study Designs | Peer-reviewed empirical journal articles and full conference papers, including case studies, prototype validations, pilot deployments, quasi-experiments, usability studies, and mixed-methods implementation studies | Reviews, editorials, opinion papers, letters, theses, protocols without results, abstracts without full paper, and grey literature |
| Outcomes | Schedule performance or schedule-relevant indicators such as progress accuracy, deviation detection, issue-resolution time, inspection efficiency, reporting latency, rework reduction, coordination quality, or decision support | Studies with no operational, managerial, or performance outcome related to monitoring/control |
| Publication Type | Peer-reviewed journal articles | Non-peer-reviewed reports, guidelines, books, chapters, blogs, or vendor notes |
| Language | English | Non-English |
| Timeframe | 2015-2025 | Studies published outside this timeframe |

2.3 Information Sources

The retrieval process was limited to research papers that had been checked by other experts and listed in databases and digital libraries most suited to construction informatics, project management, and immersive engineering applications. The main bibliographic sources consulted were the Web of Science Core Collection, Scopus, the ASCE Library, and the IEEE Xplore database. These sources were chosen for their comprehensive and complementary coverage of construction engineering, virtual and augmented reality, computer vision, building information modelling, and digital project control. To improve the retrieval of eligible open-access construction informatics studies and peer-reviewed conference papers, supplementary manual searching was also undertaken through publisher platforms and specialist outlets that regularly index relevant work. These included Taylor & Francis Online, SpringerLink, ScienceDirect, MDPI, and the Journal of Information Technology in Construction (ITcon). No grey literature sources were included. All records were exported to Zotero for de-duplication. Screening was conducted independently at the title/abstract and full-text stages, with any disagreements resolved through discussion and consensus.

2.4 Search Strategy

A combination of controlled subject terms, where available, with free-text keywords representing the PCC elements was used to develop database-specific search strategies. The search prioritised sensitivity over narrow specificity to capture the range of terminology used in construction XR research. This included terms such as “augmented reality”, “mixed reality”, “extended reality”, and “virtual reality” as well as construction monitoring terms such as“project control”, “progress monitoring”, “inspection”, schedule”, and “coordination”. Additional terms were used to capture digital integration pathways, including 'drone', 'digital twin', 'BIM', LiDAR','4D', ' 'laser scanning’, ‘SLAM', and 'computer vision'. The search was limited to English-language peer-reviewed publications from 2015 to 2025. The reference lists of eligible studies were also checked to identify further relevant records. Table 2 presents the search strings used across the main databases.

Table 2. Search strings

| Database | Search string |
| --- | --- |
| Scopus | TITLE-ABS-KEY ((construction OR building OR infrastructure OR project site) AND ("mixed reality" OR "augmented reality" OR "virtual reality" OR "extended reality" OR XR OR AR OR VR) AND (monitor* OR inspection OR progress OR coordination OR "project control" OR schedule OR "progress tracking") AND (BIM OR "building information model*" OR "4D" OR "digital twin" OR lidar OR "laser scanning" OR drone OR UAV OR SLAM OR VSLAM OR "computer vision")) AND PUBYEAR > 2014 AND PUBYEAR < 2026 AND (LIMIT-TO (LANGUAGE, "English")) |
| Web of Science Core Collection | TS=((construction OR building OR infrastructure OR "project site") AND ("mixed reality" OR "augmented reality" OR "virtual reality" OR "extended reality" OR XR OR AR OR VR) AND (monitor* OR inspection OR progress OR coordination OR "project control" OR schedule OR "progress tracking") AND (BIM OR "building information model*" OR "4D" OR "digital twin" OR lidar OR "laser scanning" OR drone OR UAV OR SLAM OR VSLAM OR "computer vision")) Refined by: English; Article or Proceedings Paper; 2015–2025 |
| IEEE Xplore | ("All Metadata":"construction" OR "building information modeling" OR BIM) AND ("All Metadata":"mixed reality" OR "augmented reality" OR "virtual reality" OR XR OR AR OR VR) AND ("All Metadata":"progress monitoring" OR inspection OR coordination OR schedule OR "project control") Filters: Journals and Conferences; English; 2015–2025 |
| ASCE Library | ("mixed reality" OR "augmented reality" OR "virtual reality" OR XR OR AR OR VR) AND (construction OR infrastructure OR building) AND ("progress monitoring" OR inspection OR coordination OR schedule OR "project control" OR "progress tracking") AND (BIM OR "4D" OR "digital twin" OR "laser scanning" OR "computer vision") Filters: Journal papers and conference papers; English; 2015–2025 |

2.5 Data Extraction and Synthesis

A standardised extraction template was used to chart the data, with refinements made after a pilot test on a small sample of relevant studies. In line with the scope of the review and the structure of the Results section, eight core variables were extracted from each included study: study identification, construction context/objective, XR system/workflow, BIM/schedule/capture integration, monitoring/control use, evaluation design, operational performance or key outcomes relevant to schedule, and implementation constraints or critical notes. This structure enabled consistent comparisons to be made across studies despite differences in project type, device configuration and evaluation method.

The synthesis was descriptive and mapping-oriented rather than effect-estimating. A numerical summary was prepared to describe the distribution of studies by XR modality, year, study design, and project setting. This was followed by a narrative thematic synthesis organised around three analytical themes derived from the extracted evidence: (1) BIM-centred XR architectures for coordination, monitoring, and inspection; (2) performance gains in progress visibility, issue resolution, schedule-relevant decision support and inspection efficiency; and (3) enabling conditions and implementation constraints, including hardware limitations, interoperability, safety, and adoption barriers. This approach enabled the review to identify patterns across the applied studies while remaining faithful to the heterogeneity of the evidence base.

3.0 Result

3.1 Screening and selection.

The PRISMA flow diagram summarises the study selection process. A total of 485 records were identified through database searches. After removing 256 duplicate records, 229 records remained for title and abstract screening. At this stage, 120 records were excluded because their titles and abstracts did not align with the review's focus. The remaining records were subjected to full-text assessment, with 80 articles being assessed for eligibility. During the full-text review, 62 articles were excluded for clearly defined reasons. These comprised 29 records that were editorial, reviews, letters, theses, protocols lacking result, opinion paper, abstract without full paper, grey literature, non-peer-reviewed report, guidelines, and chapter, book, blog or vendor notes; 13 studies that have been performed under non-construction conditions and have not been validated using XR, 14 studies where XR has been used to make stakeholder presentations, train or market, and/or performed pure laboratory, classroom or otherwise non-operational research; and six studies that reported no managerial, operational, or performance outcome After this screening procedure and eligibility, thus, 18 studies were included in the final review after meeting the inclusion criteria (Fig 1).

Figure 1. PRISMA flow diagram of study identification, screening, eligibility assessment, and inclusion for the scoping review

3.2 Summary of study characteristics.

The evidence included 18 peer-reviewed studies (Table 3), and they were published between 2018 and 2025. They were mostly applied case studies, quasi-experiments, or prototype validations, and not randomised or longitudinal field trials. Although most of the research was conducted in the field of building construction, the scope of research was also expanded to include tunnel construction, bridging, MEP installation and modular assembly. The most common modality was augmented reality, which was then followed by immersive virtual reality and mixed reality; numerous studies combined XR modes in a single workflow. The fundamental information base throughout the dataset was Building Information Modelling (BIM) which was commonly associated with 4D scheduling, computer vision, mobile applications, laser scanning, Industry Foundation Classes (IFC)/openBIM exchange, Simultaneous Localisation and Mapping (SLAM)/ Visual Simultaneous Localisation and Mapping (VSLAM), point clouds, and robotic capture. Task monitoring involved tracking progress, resolving issues, communicating the design, defect inspection, coordination, collaborative planning and documentation. The methods of evaluation often included mock-up testing, manual or traditional inspection processes, case-oriented implementation, user feedback, interviews and performance comparison with paper-based. The literature overall depicts an evidence base that is implementation-focused and methodologically heterogeneous in the present-day construction circumstances. Table 4 summarises the reported quantitative outcomes, such as inspection efficiency, reduction in coordination overhead, accuracy of progress recognition, and speed of issue resolution. It highlights where the evidence remains relevant to the schedule, but is indirect.

3.3: Results synthesis

Theme 1. BIM-centred XR architectures for monitoring, inspection, and coordination

The included studies demonstrate that, in construction, mixed reality systems are rarely standalone visual tools; rather, they are typically BIM-centred operational workflows that differ mainly in terms of how they connect schedules, models, and site data. One cluster consists of field-facing AR/MR overlays for inspection tasks and progress monitoring. Wang and Chen (2020), Kopsida and Brilakis (2020), and Lin et al. (2019) all employed real-time overlays and registration to compare planned work with actual site conditions. However, their technical approaches varied, incorporating HoloLens-based object detection, markerless 4D AR, and SLAM. Arvikar et al. (2025) built on this approach by linking optimised BIM to schedule windows, while Halder et al. (2022) incorporated live-streamed remote inspection and robotic mobility. A second cluster comprises feedback-oriented and capture-enabled systems. Khairadeen Ali et al. (2021) combined laser scanning, XR inspection, and AR feedback in a five-step office–site loop, and Kuo et al. (2025) integrated BIM, VSLAM, and AR, for defect localisation. Tan et al. (2024) built on this by coupling computer vision with BIM-linked defect management. A third cluster uses immersive VR for collaborative control rather than direct site overlay. Johansson and Roupé (2024), Tallgren et al. (2021), Khorchi and Boton (2024), and Zaker and Coloma (2018) treated VR as a coordination room for sequencing, discussing issues, and reviewing, often through IFC or 4D integration. Alhady et al. (2024) and Zaher et al. (2018) demonstrate that these workflows can be extended to infrastructure, time–cost integration, mobile devices, and GIS. However, critically, most architectures remain project-specific and are unevenly integrated into formal project control systems rather than being part of a fully closed-loop decision environment.

Theme 2. Performance gains were most evident in inspection speed, issue resolution, and progress visibility, while direct delay metrics remained limited

The most significant improvements could be seen in the speed of inspection, issue management and progress visibility, but direct performance measures were not as high. The strongest evidence in the sample is connected with operational improvements, which are closely related with schedule performance, although the endpoint is not necessarily reported in terms of formal delay reduction. According to Kopsida and Brilakis (2020), real-time progress recognition had a strong technical accuracy. They discovered a 96.5% precision, 97.3% recall, and 95.2 accuracy. This means that the MR can be useful in verifying site-state reliably. Girgin et al. (2023) provided clear evidence of the process-facing schedule. MR-based inspection has been demonstrated to yield coordination overhead reduction up to 75 percent, and MEP issue resolution up to 50 percent faster. In a similar manner, Lin et al. (2019) positioned 4D AR as a device that avoids installation errors, which lead to schedule slippage. Chalhoub and Ayer (2018) in task-execution environments discovered that MR reduced errors relative to paper-based communication, minimized the time required to interpret designs, and elevated productivity. Dallasega et al. (2023) and Melnyk et al. (2024) found time savings in documentation workflow and marking, and Tan et al. (2024) found an improvement in the inspection efficiency of 78.63%. In addition to the personal activities, Johansson and Roupé (2024), Tallgren et al. (2021), and Khorchi and Boton (2024) showed that the use of immersive VR can improve constructability reviews, shared understanding, and collaborative planning, as well as sequencing discussions. However, evidence base is still not evenly distributed. However, evidence base is still not evenly distributed. Numerous researches have used quasi-experiments, mock-ups, prototypes, surveys or case-based demonstrations instead of longitudinal controlled field trials. The literature makes a valid argument that XR enhances the quality of inspections, the speed of coordination, and visibility of progress. The evidence is however more cautious with its capacity to directly decrease project delays on a large scale.

Theme 3. Implementation success depended less on novelty and more on registration quality, workflow fit, safety, and information governance

The success of the implementation was based not on novelty but on registration quality, fit of the workflow, safety, and information governance.  The barriers to implementation also played a crucial role in the studies considered; they defined the difference between XR as a promising prototype and a tool of project-controlling. Another common technical issue was the reliability of registration and positioning. As an example, Wang and Chen (2020) needed to revise the SLAM-based indoor positioning when the construction conditions shifted. In the meantime, Kuo et al (2025) found that lighting and marker position were sensitive to performance. In spite of the high detection accuracy of Kopsida and Brilakis (2020), their methodology still relied on manual parameter optimization. The usability of hardware and the field were also thorny issues. Dallasega et al. (2023) emphasized the ergonomic risks and safety concerns related to AR headsets, whereas Melnyk et al. (2024) found the constraints in detecting inputs and hardware in tunnelling conditions. Zaker and Coloma (2018) highlighted the cost of investments and the adoption resistance, and Chalhoub and Ayer (2018) showed that, despite the improved performance of MR, users may still desire the comfort of paper-based practices. The second obstacle was information fit and interoperability. Johansson and Roupé (2024) discussed rendering issues and openBIM integration issues. Khorchi and Boton (2024) discussed this in terms of IFC and BCF workflows. Girgin et al. (2023) subtly observed that not every model's information is helpful in field inspection, and therefore, the structure of the information delivered is significant. The most plausible mitigation measures were thus practical rather than purely technological, comprising optimal BIM preparation in Arvikar et al. (2025), task-related information filtering in Girgin et al. (2023), two-step localization in Kuo et al. (2025), and office to site feedback loops in Khairadeen Ali et al. (2021).

Table 3. Included Studies Data Extraction Table

| Study | Context / objective | XR system / workflow | BIM, schedule, or capture integration | Monitoring / control use | Evaluation design | Key outcomes | Constraints / critical note |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alhady et al. (2024) | Bridge modernization; design–construction monitoring of El‑Merghani Bridge. | Integrated XR workflow using AR and VR for infrastructure visualization and simulation. | BIM linked with GIS, AASHTO road geometry, shop drawings, quantification, and Primavera P6 4D; Monte Carlo risk analysis. | Stakeholder monitoring during design and construction through immersive model interrogation. | Applied bridge case study. | Interactive 4D monitoring platform; risk analysis suggested cost-saving potential from XR use. | Schedule was hypothetical; evidence is project-specific and not a controlled field comparison. |
| Arvikar et al. (2025) | Five bridge sites; site management and real-time progress tracking. | AR-based site management with optimized full-scale BIM overlays. | Optimized BIM linked to project schedule by timeframe-based model splitting; retained Revit metadata. | Planned-versus-actual progress comparison on site. | Multi-site applied test plus survey of 30 engineers/project managers. | Supported real-time tracking across five sites; perceived as useful for efficient progress management. | Outcome evidence is largely survey-based; no direct delay-reduction metric reported. |
| Chalhoub & Ayer (2018) | Electrical construction; conduit assembly and design communication. | Mixed reality used instead of paper for communicating BIM content. | BIM content communicated through MR; no formal 4D integration stated. | Faster understanding of design intent during installation. | Quasi-experiment with 18 practitioners plus questionnaires. | Higher productivity; less time to understand design; fewer errors; more accurate assemblies than paper. | Small proof-of-concept; users still preferred paper plans despite better MR performance. |
| Dallasega et al. (2023) | MEP work in a multi-storey apartment building; lean visual management. | AR HMD supporting visual management and marking tasks. | No explicit 4D schedule integration; linked to MEP field information and marking workflow. | Improves information flow and reduces waste in execution support. | On-site case study with observations and semi-structured interviews. | Time savings; satisfactory accuracy; lower training effort; reduced resistance to visual-management adoption. | Ergonomic concerns and safety risks remained important adoption barriers. |
| Girgin et al. (2023) | MEP issue inspection and resolution during construction. | MR-based field inspection and issue-resolution workflow. | 3D MR model integrated into redesigned BPMN workflow; information filtered by task usefulness. | Detects and resolves field MEP clashes/issues faster. | Field observations, interviews, and workflow modelling. | Up to 75% lower coordination overhead and at least 50% faster issue resolution; better installation quality anticipated. | Some model information was not useful in the field; partly process-modelled rather than long-term comparative evidence. |
| Halder et al. (2022) | Remote progress inspection of construction sites. | Quadruped robot plus AR plus 360° live stream plus cloud control. | Real-time comparison between as-built video stream and as-planned BIM geometry. | Remote real-time monitoring without repeated physical walkthroughs. | Framework implementation tested in two use cases. | Enabled more frequent and accessible progress data collection; improved inspection reach. | Experimental rather than routine field deployment; depends on robot, cloud, and connectivity performance. |
| Johansson & Roupé (2024) | Several real-world projects; coordination, planning, and constructability review. | Single-user and multi-user immersive VR in openBIM environment. | Direct import from IFC models; co-located and remote multi-user sessions. | Design review, sequencing discussion, and pre-production issue detection. | Real-world evaluation across several projects. | Improved communication, understanding, collaboration, sequencing, and alternative design exploration. | Main limits were rendering performance and interoperability. |
| Khairadeen Ali et al. (2021) | Indoor construction progress monitoring; office-to-site inspection loop. | iVR system with five modules: locate, scan, prepare, inspect, feedback. | 3D laser scanning plus XR plus visual programming; AR-based feedback to site. | Near-real-time progress and quality assessment for remote inspection. | Experimental lab test. | Successfully exchanged required information between site and office; supports progress assessment and decision-making. | Indoor and lab-based validation; limited evidence on large-scale field deployment. |
| Khorchi & Boton (2024) | Coordination meetings and 4D collaborative review. | VR environment with 4D simulation and BCF exchange. | IFC-compliant 3D model plus planning schedule plus BCF collaboration support. | 4D coordination meetings in immersive environment. | Method plus prototype development and validation. | Demonstrated feasibility of 4D simulation-based collaboration in VR; identified lessons learned. | Prototype-stage evidence; site-level schedule gains were not directly quantified. |
| Kopsida & Brilakis (2020) | Interior construction progress inspection. | HoloLens MR with real-time as-built versus as-planned comparison. | Automated detection of volumetric objects while inspector walks through site. | Real-time progress inspection for deviation detection. | System and algorithm testing with parameter optimization. | 95.2% accuracy, 96.5% precision, and 97.3% recall. | Strong technical validation, but broader managerial and project-level delay effects were not directly measured. |
| Kuo et al. (2025) | Construction defect inspection and quality management. | BIM plus AR plus VSLAM prototype for defect recording. | Two-phase positioning: visual markers plus real-time VSLAM; photo/note defect logging in BIM; works offline. | Faster and more precise site inspection and defect localization. | Prototype development and validation. | Improved inspection accuracy and efficiency; enabled offline inspection support. | Sensitive to lighting, marker placement, and environmental conditions. |
| Lin et al. (2019) | Modular construction installation monitoring. | Real-time 4D AR with markerless registration. | 4D BIM linked directly to as-built view without prior point-cloud reconstruction. | Assembly sequence monitoring and early error prevention. | Prototype validated with mock-up components. | Helped avoid possible errors; supported assembly sequence monitoring and schedule control. | Validation used mock-up scale rather than full live project deployment. |
| Melnyk et al. (2024) | Conventional tunnelling; anchor inspection reporting. | AR prototype for digital inspection documentation. | Digital AR reporting workflow; BIM link not explicit in abstract. | Faster inspection documentation and quality management. | Design Science Research plus prototype plus tunnel case study. | Documentation was faster than paper-based process; supports real-world quality management. | Input-detection issues and current hardware limitations persisted. |
| Tallgren et al. (2021) | Collaborative planning and scheduling in construction. | Multi-user VR for 4D collaborative planning and scheduling. | BIM plus schedule plus process modelling integrated into virtual planning system. | Social co-creation of planning/scheduling and 4D modelling. | Process mapping plus system implementation. | Improved project understanding and shared planning/scheduling understanding. | Evidence is mainly process and collaboration oriented, with no direct hard time metric. |
| Tan et al. (2024) | Building defect inspection and defect data management. | Computer vision plus ARDI plus BIM-based defect data management. | YOLOv5 plus DeepSORT; 2D–3D defect mapping synchronized with BIM. | Real-time defect detection, measurement, tracking, and management. | Framework tested in two experiments. | Centimeter-level precision and 78.63% improvement in inspection efficiency over manual inspection. | Strong inspection evidence, but not a full project-wide progress-control study. |
| Wang & Chen (2020) | On-site progress monitoring in changing indoor conditions. | AR plus BIM system using SLAM, point-cloud mapping, and plane detection. | 3D BIM superimposed on real scene; indoor positioning updated as construction changes. | On-site progress data collection, monitoring, and performance evaluation. | System development and proposed method. | Enabled real-time progress monitoring and visual feedback in dynamic site conditions. | Abstract reports system capability rather than quantified field outcome metrics. |
| Zaher et al. (2018) | Construction progress tracking with smartphones. | Mobile AR through BIM-U and BIM-Phase. | On-site updates feed a 4D BIM linked with earned value, actual cost, and planned value. | Handheld progress, time, and cost monitoring during construction. | Methodology/system paper. | Demonstrated potential for integrating time/cost tracking with mobile AR-based progress monitoring. | Abstract gives limited empirical performance data; results are framed as potential rather than hard effect sizes. |
| Zaker & Coloma (2018) | Real-project collaboration and design review. | VR-integrated BIM workflow with task simulation. | Uses actual project BIM models in immersive collaborative environment. | Collaboration, design review, and practical clash-detection simulation. | Real-project case study with participant feedback. | Reported benefits for collaboration; simulated clash detection appeared practically useful. | Barriers included hardware/software investment and resistance to adoption. |

| Table 4. Quantitative comparison of reported performance gains across included studies |  |  |  |  |
| --- | --- | --- | --- | --- |
| Study | System/task | Metric | Reported result | Interpretation |
| Girgin et al. (2023) | MR field inspection | Coordination overhead | Up to 75% reduction | Schedule-relevant proxy |
| Girgin et al. (2023) | MR field inspection | Issue-resolution speed | At least 50% faster | Schedule-relevant proxy |
| Kopsida & Brilakis (2020) | MR progress monitoring | Accuracy | 95.2% | Technical performance |
| Kopsida & Brilakis (2020) | MR progress monitoring | Precision | 96.5% | Technical performance |
| Kopsida & Brilakis (2020) | MR progress monitoring | Recall | 97.3% | Technical performance |
| Tan et al. (2024) | AR + CV defect inspection | Inspection efficiency | 78.63% improvement | Operational performance |
| Hou et al. (2015) | AR assembly support | Task completion time | 50% reduction | Experimental comparator literature |
| Hou et al. (2015) | AR assembly support | Assembly errors | 50% reduction | Experimental comparator literature |
| Hou et al. (2015) | AR assembly support | Rework time | 46% reduction | Experimental comparator literature |
| Hou et al. (2015) | AR assembly support | Correction cost | 66% reduction | Experimental comparator literature |
| Note: This table summarizes the clearest quantitative outcomes reported across the evidence base. Most measures are schedule-relevant proxies rather than direct project-level delay-reduction metrics. |  |  |  |  |

4.0 Discussion

4.1 Summary of key findings

In the studies included, XR systems were observed to have the most significant positive impacts on enhancing operational mechanisms that affect schedule performance, as opposed to actual evidence of delay reduction at the project level. The greatest advances were on the basis of faster inspections, real-time or near-real-time progress visibility, better design communication and more efficient coordination. Mixed reality inspection of MEP problems minimised coordination overhead up to 75% and speed of issue resolution at least 50 times, and AR based defect inspection delivered high positional accuracy and significant efficiency. Earlier detection of installation or sequencing errors, high technical accuracy and better planned versus actual comparisons were also recorded by real-time MR and AR progress monitoring systems. VR research showed that constructability reviews, joint planning, remote coordination, and creation of a shared understanding were valuable, especially when combined with openBIM or 4D workflow. Nonetheless, the evidence base was still weak because of dependency on prototypes, small samples, lack of long-term field tests, and mock-ups. The persistent barriers involved safety, interoperability, ergonomics, resistance to the user, sensitivity to the light and the cost of the hardware.

4.2 (Comparison of Findings with Global Literature)

The review builds on the current international XR literature by proving that, despite the increased operational integration of construction monitoring systems, they are not yet closed-loop control platforms. According to Alsafouri and Ayer (2018), most applications included tended to relay the information in BIM or schedules to the site through AR overlays, VR coordination rooms, or the MR dashboard. Automated bi-directional feedback was, however, uncommon. This trend is also in line with the works by Delgado et al. (2020), Alizadehsalehi et al. (2020), and Amin et al. (2023), who argue that the maturity of BIM-XR hinges on not just visualisation, but also solid positioning, collaboration, interaction, integration functions, and automation. The reviewed studies propose architectural progress that could be measured in comparison with the broader body of literature, especially in cases where BIM was also associated with computer vision or 4D simulation, laser scanning, SLAM and VSLAM. Nevertheless, interoperability was not even, and much of the workflow was still a prototype and not enterprise-ready.

The studies included found the greatest benefits in the areas of progress inspection efficiency, visibility, speed of coordination, and issue resolution. But there was no direct evidence of the reduction of delay at the project level. This aligns with the conclusions of Chen et al. (2020), Hou et al. (2015), Kwiatek et al. (2019), and Sabzevar et al. (2023), who established that AR improves information access and its understanding, increases assembly accuracy, and efficiency of the work compared with paper-based or traditional techniques. Nevertheless, it also corroborates the results of Luo et al. (2022) and Getuli et al. (2020) that workplace planning, inspection, and quality support tend to experience digital gains more than the direct outcomes of schedule measures. The current review confirms the results of Pal et al. (2023) in that regard. XR-enabled oversight is moving towards being driven by digital-twin logic, although predictive, constantly updated progress control is an aspiration, but not a standard one.

The quality of registration, ergonomics, synchronisation, safety, and barriers to adoption were frequently mentioned as the issues of concern in the reviewed studies and closely reflect the concerns expressed by Qureshi et al. (2022), Kolaei et al. (2022), and Maqsoom et al. (2023). In the same way, Alirezaei et al. (2022) showed that, even though AR can enhance schedule risk management and cost, users continue to face interface and subsystem coordination problems. Garbett et al. (2021) also propose an idea that team-based XR adoption relies on cloud-based collaboration instead of one-on-one visualisation. In general, our results thus support the current global literature that XR can enhance decision support and field communication but its effect of schedules is determined by its interoperable data exchange, workflow redesign, and site-ready hardware in the conditions of regular projects and various construction sites worldwide.

4.3 Practice and Policy Implications

Policy:  It is suggested that mixed reality enabled construction monitoring is not only to be relocated out of individual pilot applications, but it is also to be integrated into a managed digital standard of project monitoring and control. To realise this, there is a need to have clear expectation on interoperability between 4D scheduling tools, capture technologies, BIM and field-based visualisation systems amongst clients and regulators. Registration accuracy, metadata consistency, model version control and decision audit trails should also have defined requirements. MR provisions must be integrated into common data environment procedures and project reporting standards and digital construction protocols. Meanwhile, specific performance pointers must be defined, such as the number of intended and actual updates, inspection cycle period, credibility of model-to-site correspondence, and the duration of issue resolution and reporting thoroughness. There is also a need of common data standards, practical guidelines on how to use the devices and rules to govern scans, images and other data taken in the field. On the lower-resource environment, scalable, mobile-first, and task-specific MR applications with the assistance of phased implementation plans, streamlined BIM preparation processes, and remote coordination alternatives in terms of technical assistance and follow-up should be prioritized.

Practice implication: Practically, the introduction of MR should be presented as a structured workflow, namely, registration, comparison, capture, monitoring, and action. This includes making sure site data is captured in time, comparison of planned work and actual work is done in a disciplined way, effective alignment with BIM and timely escalation of deviations that need redress. MR must be given priority in task-specific applications where it can provide immediate benefit, especially in MEP coordination, progress verification, tracking interior fit-out tracking, defect inspection and collaborative 4D review of critical work packages. Effective implementation is also reliant on pragmatic support functions, i.e., role-based information filtering, short-cycle training, basic field feedback logs and convincing device use protocols. MR should not be implemented as a single visualisation tool or demonstration without the connection to issue management, short-term planning systems, and reporting routines. Its application must reflect the project phase, site complexity, trade- interface density, and the urgency of schedule-control decisions. Indicators should be used to trace performance, like issue closure rate, rate of rework, inspection turnaround time, consistency of planned work completion, and reporting latency, and these measures should be a continual input to the continuous improvement. The site teams and the management will need to be trained on model interpretation, digital inspection, safe use of devices and exception-based reporting in order to enhance reliability, adoption, and fair implementation across projects.

4.4 Future research directions

Future research should move decisively beyond proof-of-concept demonstrations and focus on determining whether mixed reality can consistently provide valuable insights that are relevant to decision-making under routine project conditions. A key priority should be the development of longitudinal, field-based studies examining performance across project phases, rather than at isolated implementation moments. This is essential if the literature is to progress from demonstrating technical feasibility to establishing operational validity. A second priority is the adoption of more comparable and rigorous outcome frameworks. Studies are now needed that measure not only inspection speed, coordination quality or visibility, but also response time to deviations, schedule adherence, incidence of rework, and consequences for subsequent projects. Thirdly, rather than a secondary technical consideration, research should address system integration as a central issue. More attention must be given to how mixed reality interfaces with, digital twins, 4D planning, BIM, sensing systems and production control environments in real time. Further work is also required on human factors, safe deployment, governance, and role-specific information design.

4.5 Limitations of Review

The evidence base was extremely diverse and comparatively small, including various project settings, monitoring goals, study designs, and XR applications. This complicated direct comparison. A large fraction of the studies included were case studies, controlled tests, or prototype tests, but not in long-term real-world project settings. Furthermore, the majority of the studies concentrated on the indirect metrics, including the enhancement of coordination or inspection efficiency, without providing definite measures of schedule reduction. The limitation on access to open-access studies could also have led to the exclusion of other peer-reviewed studies that were relevant.

5.0 Conclusion

This scoping review analysed 18 empirical studies utilising mixed reality in construction monitoring, coordination, inspection, and scheduling. Workflows through MR, AR, and VR related to BIM, site-capture technologies, 4D scheduling, and other project-related activities typically enhance the visibility of progress, inspection efficiency, team decision-making, and issue resolution in a multitude of project settings. However, direct schedule reduction was still not well evidenced. The majority of reported applications were prototyped or case studies, and only a small number were tightly integrated into daily project control systems. The results indicate that the mixed reality may facilitate more effective schedule-oriented monitoring in case they are supported by sound data capture, feasible site application, and interoperable workflows. Future studies must emphasize the validation in the longer perspective and comparisons between the projects and the closer integration with production control systems and digital twins.

COMPETING INTERESTS DISCLAIMER:

Authors have declared that they have no known competing financial interests OR non-financial interests OR personal relationships that could have appeared to influence the work reported in this paper.

Disclaimer (Artificial intelligence)

Author(s) hereby declare that NO generative AI technologies such as Large Language Models (ChatGPT, COPILOT, etc.) and text-to-image generators have been used during the writing or editing of this manuscript.

References

- Alhady, A., Alanany, M., Khodair, Y. et al. Integrating building information modelling (BIM) and extended reality (XR) in the transportation infrastructure industry. ABEN 5, 22 (2024). https://doi.org/10.1186/s43251-024-00132-6

- Alirezaei, S., Taghaddos, H., Ghorab, K., Tak, A. N., & Alirezaei, S. (2022). BIM-augmented reality integrated approach to risk management. Automation in Construction, 141, 104458. https://doi.org/10.1016/j.autcon.2022.104458

- Alizadehsalehi, S., Hadavi, A., & Huang, J. C. (2020). From BIM to extended reality in AEC industry. Automation in construction, 116, 103254. https://doi.org/10.1016/j.autcon.2020.103254

- Alsafouri, S., & Ayer, S. K. (2018). Review of ICT implementations for facilitating information flow between virtual models and construction project sites. Automation in Construction, 86, 176-189. https://doi.org/10.1016/j.autcon.2017.10.005

- Amin, K., Mills, G., & Wilson, D. (2023). Key functions in BIM-based AR platforms. Automation in Construction, 150, 104816. https://doi.org/10.1016/j.autcon.2023.104816

- Arvikar, S., Aung, P. P. W., Cha, G., & Park, S. (2025). Augmented Reality-based construction site management using optimized BIM and project schedule integration. Automation in Construction, 175, 106204. https://doi.org/10.1016/j.autcon.2025.106204

- Begić, H., Galić, M., & Dolaček-Alduk, Z. (2022). Digitalization and automation in construction project's life-cycle: A review.

- Chalhoub, J., & Ayer, S. K. (2018). Using Mixed Reality for electrical construction design communication. Automation in construction, 86, 1-10.

- Chen, Y. J., Lai, Y. S., & Lin, Y. H. (2020). BIM-based augmented reality inspection and maintenance of fire safety equipment. Automation in Construction, 110, 103041. https://doi.org/10.1016/j.autcon.2019.103041

- Dallasega, P., Schulze, F., & Revolti, A. (2023). Augmented Reality to overcome Visual Management implementation barriers in construction: a MEP case study. Construction management and economics, 41(3), 232-255. https://doi.org/10.1080/01446193.2022.2135748

- Delgado, J. M. D., Oyedele, L., Demian, P., & Beach, T. (2020). A research agenda for augmented and virtual reality in architecture, engineering and construction. Advanced Engineering Informatics, 45, 101122. https://doi.org/10.1016/j.aei.2020.101122

- Durdyev, S., & Hosseini, M. R. (2020). Causes of delays on construction projects: a comprehensive list. International journal of managing projects in business, 13(1), 20-46. https://doi.org/10.1108/IJMPB-09-2018-0178

- Ekanayake, B., Wong, J. K. W., Fini, A. A. F., & Smith, P. (2021). Computer vision-based interior construction progress monitoring: A literature review and future research directions. Automation in construction, 127, 103705. https://doi.org/10.1016/j.autcon.2021.103705

- Forcael, E., Ferrari, I., Opazo-Vega, A., & Pulido-Arcas, J. A. (2020). Construction 4.0: A literature review. Sustainability, 12(22), 9755. https://doi.org/10.3390/su12229755

- Garbett, J., Hartley, T., & Heesom, D. (2021). A multi-user collaborative BIM-AR system to support design and construction. Automation in Construction, 122, 103487. https://doi.org/10.1016/j.autcon.2020.103487

- Getuli, V., Capone, P., Bruttini, A., & Isaac, S. (2020). BIM-based immersive Virtual Reality for construction workspace planning: A safety-oriented approach. Automation in Construction, 114, Article 103160. https://doi.org/10.1016/j.autcon.2020.103160

- Girgin, S., Fruchter, R., & Fischer, M. (2023). A case study towards assessing the impact of mixed reality-based inspection and resolution of MEP issues during construction. Journal of Information Technology in Construction, 28.

- Halder, S., Afsari, K., Serdakowski, J., DeVito, S., Ensafi, M., & Thabet, W. (2022). Real-Time and Remote Construction Progress Monitoring with a Quadruped Robot Using Augmented Reality. Buildings, 12(11), 2027. https://doi.org/10.3390/buildings12112027

- Hasan, S., & Sacks, R. (2023). Integrating BIM and Multiple Construction Monitoring Technologies for Acquisition of Project Status Information. Journal of Construction Engineering and Management, 149(7), Article 04023051. https://doi.org/10.1061/JCEMD4.COENG-12826

- Hou, L., Wang, X., & Truijens, M. (2015). Using augmented reality to facilitate piping assembly: an experiment-based evaluation. Journal of Computing in Civil Engineering, 29(1), 05014007. https://doi.org/10.1061/(ASCE)CP.1943-5487.000034

- Johansson, M., & Roupé, M. (2024). Real-world applications of BIM and immersive VR in construction. Automation in Construction, 158, 105233. https://doi.org/10.1016/j.autcon.2023.105233

- Khairadeen Ali, A., Lee, O. J., Lee, D., & Park, C. (2021). Remote Indoor Construction Progress Monitoring Using Extended Reality. Sustainability, 13(4), 2290. https://doi.org/10.3390/su13042290

- Khorchi, A., & Boton, C. (2024). An OpenBIM-based 4D approach to support coordination meetings in virtual reality environments. Journal of building engineering, 85, 108647. https://doi.org/10.1016/j.jobe.2024.108647

- Klinc, R., & Turk, Ž. (2019). Construction 4.0 – Digital Transformation of One of the Oldest Industries. Economic and Business Review, 21(3). https://doi.org/10.15458/ebr.92

- Kolaei, A. Z., Hedayati, E., Khanzadi, M., & Amiri, G. G. (2022). Challenges and opportunities of augmented reality during the construction phase. Automation in Construction, 143, 104586.  https://doi.org/10.1016/j.autcon.2022.104586

- Kopsida, M., & Brilakis, I. (2020). Real-time volume-to-plane comparison for mixed reality–based progress monitoring. Journal of Computing in Civil Engineering, 34(4), 04020016. https://doi.org/10.1061/(ASCE)CP.1943-5487.000089

- Kwiatek, C., Sharif, M., Li, S., Haas, C., & Walbridge, S. (2019). Impact of augmented reality and spatial cognition on assembly in construction. Automation in construction, 108, 102935. https://doi.org/10.1016/j.autcon.2019.102935

- Kuo, W.-L., Huang, B.-K., Hsieh, S.-H., Tsai, Y.-H., & Chang, Y.-T. (2025). Integration of BIM and ar with VSLAM to assist in construction site inspection. Journal of Civil Engineering and Management, 31(6), 646–669. https://doi.org/10.3846/jcem.2025.24360

- Lin, Z. Y., Petzold, F., & Ma, Z. L. (2019). A real-time 4D augmented reality system for modular construction progress monitoring. In ISARC. Proceedings of the International Symposium on Automation and Robotics in Construction (Vol. 36, pp. 743-748). IAARC Publications.

- Luo, H., Lin, L., Chen, K., Antwi-Afari, M. F., & Chen, L. (2022). Digital technology for quality management in construction: A review and future research directions. Developments in the Built Environment, 12, 100087. https://doi.org/10.1016/j.dibe.2022.100087

- Maqsoom, A., Zulqarnain, M., Irfan, M., Ullah, F., Alqahtani, F. K., & Khan, K. I. A. (2023). Drivers of, and barriers to, the adoption of mixed reality in the construction industry of developing countries. Buildings, 13(4), 872. https://doi.org/10.3390/buildings13040872

- Melnyk, O., Huymajer, M., Fenzl, D., Huemer, C., Wenighofer, R., & Mazak-Huemer, A. (2024). Augmented reality for enhanced documentation and anchor inspection reporting in conventional tunnelling. Tunnelling and Underground Space Technology, 153, 106040. https://doi.org/10.1016/j.tust.2024.106040

- Omrany, H., Al-Obaidi, K. M., Husain, A., & Ghaffarianhoseini, A. (2023). Digital twins in the construction industry: a comprehensive review of current implementations, enabling technologies, and future directions. Sustainability, 15(14), 10908.

- Pal, A., Lin, J. J., Hsieh, S. H., & Golparvar-Fard, M. (2023). Automated vision-based construction progress monitoring in built environment through digital twin. Developments in the Built Environment, 16, 100247. https://doi.org/10.1016/j.dibe.2023.100247

- Paneru, S., & Jeelani, I. (2021). Computer vision applications in construction: Current state, opportunities & challenges. Automation in Construction, 132, 103940. https://doi.org/10.1016/j.autcon.2021.103940

- Qureshi, A. H., Alaloul, W. S., Wing, W. K., Saad, S., Ammad, S., & Musarat, M. A. (2022). Factors impacting the implementation process of automated construction progress monitoring. Ain Shams Engineering Journal, 13(6), 101808. https://doi.org/10.1016/j.asej.2022.101808

- Sabzevar, M. F., Gheisari, M., & Lo, L. J. (2023). AR-QR code for improving crew access to design and construction information. Automation in Construction, 154, 105017. https://doi.org/10.1016/j.autcon.2023.105017

- Sami Ur Rehman, M., Shafiq, M. T., & Ullah, F. (2022). Automated computer vision-based construction progress monitoring: a systematic review. Buildings, 12(7), 1037.https://doi.org/10.3390/buildings12071037

- Tallgren, M. V., Roupé, M., & Johansson, M. (2021). 4D modelling using virtual collaborative planning and scheduling. Journal of information Technology in Construction (itcon), 26(42), 763-782.

- Tan, Y., Xu, W., Chen, P., & Zhang, S. (2024). Building defect inspection and data management using computer vision, augmented reality, and BIM technology. Automation in Construction, 160, 105318. https://doi.org/10.1016/j.autcon.2024.105318

- Viles, E., Rudeli, N. C., & Santilli, A. (2020). Causes of delay in construction projects: a quantitative analysis. Engineering, Construction and Architectural Management, 27(4), 917-935. https://doi.org/10.1108/ECAM-01-2019-0024

- Wang, T., & Chen, H. M. (2023). Integration of building information modeling and project management in construction project life cycle. Automation in Construction, 150, 104832. https://doi.org/10.1016/j.autcon.2023.104832

- Wang, S. K., & Chen, H. M. (2020). A construction progress on-site monitoring and presentation system based on the integration of augmented reality and BIM. In ISARC. Proceedings of the International Symposium on Automation and Robotics in Construction (Vol. 37, pp. 147-154). IAARC Publications. https://doi.org/10.22260/ISARC2020/0023

- Zaher M, Greenwood D, Marzouk M (2018), "Mobile augmented reality applications for construction projects". Construction Innovation: Information Process Management, Vol. 18 No. 2 pp. 152–166, doi: https://doi.org/10.1108/CI-02-2017-0013

- Zaker, R., Coloma, E. Virtual reality-integrated workflow in BIM-enabled projects collaboration and design review: a case study. Vis. in Eng. 6, 4 (2018). https://doi.org/10.1186/s40327-018-0065-6

- Zhong, B., Wu, H., Ding, L., Love, P. E., Li, H., Luo, H., & Jiao, L. (2019). Mapping computer vision research in construction: Developments, knowledge gaps and implications for research. Automation in Construction, 107, 102919. https://doi.org/10.1016/j.autcon.2019.102919